## Roadmap
Enterprise AI Agent Programme - Delivery Roadmap (AWS)
Kickoff 17 Jun 2026 - Go-live 16 Nov 2026 (5-month delivery window)
Phase | Start | End | Jun 2026 | Jul 2026 | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026
Phase 1 - Administrative AI Agent (MVP) | 17 Jun | 16 Jul
Phase 2 - Action Tracking Agent | 17 Jul | 16 Aug
Phase 3 - Governance & Forum Agent | 17 Jul | 16 Sep
Phase 4 - Reporting & Analytics Agent | 17 Aug | 16 Oct
Phase 5 - Enterprise Knowledge Agent | 17 Sep | 16 Oct
Phase 6 - Central Control Tower (Orchestration) | 17 Sep | 16 Nov
Key Milestones |  |  |  | MVP live (16 Jul) |  | Governance insights (16 Sep) | Knowledge Q&A (16 Oct) | Control Tower go-live (16 Nov)
Columns are calendar months. Shaded = phase active that month. Cross-cutting from kickoff: Security & IAM, cost governance, data privacy/PII, CI/CD, human-in-the-loop review.

## Phase Plan
Phase | Start Date | End Date | Duration | Owner | Objective | Core AWS Services | Key Deliverables
Phase 1 - Administrative AI Agent (MVP) | 17 Jun 2026 | 16 Jul 2026 | 1 mo | AI/ML Lead | Automate meeting admin: transcripts to minutes, actions, owners, due dates | Amazon Transcribe Amazon Bedrock Amazon S3 DynamoDB AWS Lambda | Meeting minutes Action register Summary report Dashboard updates
Phase 2 - Action Tracking Agent | 17 Jul 2026 | 16 Aug 2026 | 1 mo | Automation Eng | Monitor, remind, escalate and report on open / overdue actions | Amazon EventBridge Amazon SES / SNS DynamoDB AWS Lambda | Weekly action reports Overdue alerts Escalation notifications
Phase 3 - Governance & Forum Agent | 17 Jul 2026 | 16 Sep 2026 | 2 mo | Data Eng | Read SteerCo / CIO / Cyber / Risk / Audit outputs; detect themes & risks | Amazon Bedrock Bedrock Knowledge Bases Amazon S3 AWS Lambda | Governance dashboard Executive reports Risk insights
Phase 4 - Reporting & Analytics Agent | 17 Aug 2026 | 16 Oct 2026 | 2 mo | BI Lead | Consolidate reports, measure delivery, build CIO packs & trend analysis | Amazon QuickSight AWS Glue Amazon Athena Amazon S3 | QuickSight dashboards Monthly reports CIO packs Trend analysis
Phase 5 - Enterprise Knowledge Agent | 17 Sep 2026 | 16 Oct 2026 | 1 mo | AI/ML Lead | Searchable organisational memory; natural-language Q&A over all outputs | Bedrock Knowledge Bases OpenSearch Serverless Amazon Bedrock (RAG) | Searchable knowledge base Q&A assistant Decision history
Phase 6 - Central Control Tower (Orchestration) | 17 Sep 2026 | 16 Nov 2026 | 2 mo | Solutions Architect | Connect all agents through a central platform - the "spine" | Amazon Bedrock Agents AWS Step Functions API Gateway Amazon Cognito | Unified orchestration platform Agent registry Central console

## Detailed Tasks
Phase | Start | End | Workstream / Task | AWS Service | Output
Phase 1 | 17 Jun | 16 Jul | Set up AWS landing zone, IAM roles, S3 buckets for raw inputs | S3, IAM, Organizations | Secure ingest foundation
Phase 1 | 17 Jun | 16 Jul | Transcribe recordings to text; ingest Teams transcripts & notes | Amazon Transcribe, S3 | Normalised transcript store
Phase 1 | 17 Jun | 16 Jul | Extract actions/owners/due dates; minutes, summaries, register | Amazon Bedrock, DynamoDB | MVP live (minutes + register)
Phase 2 | 17 Jul | 16 Aug | Scheduled scan of open/overdue actions; reminder + escalation logic | EventBridge, Lambda | Automated reminders
Phase 2 | 17 Jul | 16 Aug | Notification channels and closure-evidence capture | Amazon SES / SNS, S3 | Alerts & status reports
Phase 3 | 17 Jul | 16 Sep | Ingest SteerCo/CIO/Cyber/Risk/Audit outputs into knowledge base | Bedrock Knowledge Bases, S3 | Governance corpus
Phase 3 | 17 Aug | 16 Sep | Theme, risk & dependency detection; executive summaries | Amazon Bedrock, Lambda | Risk insights & exec reports
Phase 4 | 17 Aug | 16 Sep | Build data lake / ETL for reporting; define KPIs & metrics | AWS Glue, Athena, S3 | Curated reporting datasets
Phase 4 | 17 Aug | 16 Oct | Dashboards, monthly reports, CIO packs, trend analysis | Amazon QuickSight | Executive reporting packs
Phase 5 | 17 Sep | 16 Oct | Index all outputs; build vector store for semantic search | OpenSearch Serverless, S3 | Searchable index
Phase 5 | 17 Sep | 16 Oct | RAG-based Q&A assistant over organisational memory | Bedrock Knowledge Bases (RAG) | Natural-language Q&A
Phase 6 | 17 Sep | 16 Oct | Design orchestration spine; agent registry & shared data contracts | Step Functions, API Gateway | Orchestration design
Phase 6 | 17 Oct | 16 Nov | Wire all agents together; central console & access control | Bedrock Agents, Cognito | Unified platform
Phase 6 | 17 Oct | 16 Nov | End-to-end testing, hardening, go-live & handover | CloudWatch, Step Functions | Production Control Tower